## Sheet1
Sprint#1 Burndown chat
Task ID | Task Name | Expect Time | Day 1 | Day2 | Day3
1 | Identify project goals and success criteria | 1 | 1
2 | Define system boundaries (what is included and excluded) | 1 | 1
3 | Write a short project scope description | 1 | 1
4 | List all possible POS system functions | 1 | 1
5 | Identify core features (sale processing and return handling) | 1 | 1
6 | Write user stories for each core feature | 1 |  | 1
7 | Ensure user stories follow the standard format | 1 |  | 1
8 | Review and refine user stories as a team | 1 |  | 1
9 | Decide sprint length | 1 |  | 1
10 | Group tasks into Sprint 1 and Sprint 2 | 1 |  | 1
| Total | 10
| Expect complete time | 10 | 5 | 0 | 0
| Actual completet time | 10 | 3 | 5 | 2
| Actual | 7 | 2 | 0
| Expect | 5 | 0 | 0